## Q2-2023
Week | Backend | Complexity estimation | Frontend | Complexity estimation
2023-04-03 | Setup source control on GitHub | low | Setup source control on GitHub | low
2023-04-10 | Create build system (CI) | low | Create build system (CI) | low
2023-04-17 | Create build system (CD) | intermediate | Create build system (CI) | intermediate
2023-04-24 | Specify API | intermediate | Build simple UI | intermediate
2023-05-01 | Mock API that returns no data | intermediate | Frontend communicates with backend | low
2023-05-08 | Implement API | high | Specify layout | low
2023-05-15 | Implement API | high | Integrate API calls | intermediate
2023-05-22 | Enhance logging | low | Integrate API calls | intermediate
2023-05-29 | Add more automated testing | intermediate | Build decent UI | high
2023-06-05 | Ready for QA | intermediate | Ready for QA | intermediate
2023-06-12 | Testing | intermediate | Testing | intermediate
2023-06-19 | Testing | intermediate | Testing | intermediate
| Goals |  | Goals
| Build a ML API |  | deployed on Azure
| Decent Logging output |  | Build on Angular

## yearly 23-24
Quarter | Backend | Complexity estimation | Frontend | Complexity estimation
Q3 2023 | Extend the API to make the prediction model selectable from the REST request | intermediate | Enhance the UI to support making prediction from the homepage with user input | intermediate
Q4 2023 | Automate infrastructure setup using terraform | intermediate
Q1 2024 | Support uploading of prediction models and allow "abstract" prediction Request | high | Support uploading prediction models and "abstract" prediciton Requests | high
Q2 2024 | Make infrastructure scalable | low
| Goals |  | Goals
| Have a more or less generic backend supporting an prediction models and user input variables for the prediction model |  | Have a very handy web gui to work with any given prediction model and custom input variables for that model