## Q2-2023
Week | Backend | Complexity estimation | Frontend | Complexity estimation
2023-04-03 | Setup source control on GitHub | low | Setup source control on GitHub | low
2023-04-10 | Create build system (CI) | low | Create build system (CI) | low
2023-04-17 | Create build system (CD) | intermediate | Create build system (CI) | intermediate
2023-04-24 | Specify API | intermediate | Build simple UI | intermediate
2023-05-01 | Mock API that returns no data | intermediate | Frontend communicates with backend | low
2023-05-08 | Implement API | high | Specify layout | low
2023-05-15 | Implement API | high | Integrate API calls | intermediate
2023-05-22 | Enhance logging | low | Integrate API calls | intermediate
2023-05-29 | Add more automated testing | intermediate | Build decent UI | high
2023-06-05 | Ready for QA | intermediate | Ready for QA | intermediate
2023-06-12 | Testing | intermediate | Testing | intermediate
2023-06-19 | Testing | intermediate | Testing | intermediate
| Goals |  | Goals
| Build a ML API |  | deployed on Azure
| Decent Logging output |  | Build on Angular